## Sheet1
Risk ID | Risk Description | Adversarial / Non-Adversarial | Consequences | Existing Controls | Vendor ID | Vendor | Likelihood | Impact | Risk Score | Risk Treatment | Treatment Plan | Risk Owner | Residual Risk | Residual Risk Score
R001 | Regulatory Non-Compliance | Non-adversarial | Regulatory penalties and fines; License suspensions or restrictions; Reputational damage; Increased regulatory scrutiny. | Vendor due diligence and compliance assessment (ISO 27001 A.15); Contractual compliance clauses and SLAs; Periodic audits and certifications review; Regulatory monitoring and reporting | V01 | Amazon Web Services | 3 | 4 | 12 | Mitigate | Ensure compliance certifications (ISO, SOC) | Compliance Officer | Low | 6
[5 empty] | V02 | Temenos | 3 | 5 | 15 | Mitigate | Regulatory reporting checks, audit controls |  | Medium | 8
[5 empty] | V03 | Razorpay | 3 | 5 | 15 | Mitigate | Ensure PCI + RBI compliance validation, periodic audits |  | Medium | 8
[5 empty] | V07 | Onfido | 3 | 5 | 15 | Mitigate | KYC compliance validation, periodic reviews |  | Medium | 8
[5 empty] | V09 | Plaid | 3 | 5 | 15 | Mitigate | Data-sharing compliance checks, legal review |  | Medium | 8
[5 empty] | V11 | Microsoft Azure | 3 | 4 | 12 | Mitigate | Regulatory compliance alignment, audit reports |  | Low | 6
R002 | PCI-DSS Non-Compliance | Non-adversarial | Heavy financial penalties; Loss of ability to process card payments; Customer trust erosion | PCI-DSS compliant payment processing (for Razorpay); Encryption of cardholder data (A.10); Network segmentation and secure transmission; Regular vulnerability scans and audits | V01 | Amazon Web Services | 2 | 4 | 8 | Mitigate | Restrict CHD storage, secure configs | InfoSec Head | Very Low | 3
[5 empty] | V03 | Razorpay | 3 | 5 | 15 | Mitigate |  |  | Medium | 8
[5 empty] | V06 | Cloudflare | 2 | 4 | 8 | Mitigate | Secure traffic routing, TLS enforcement |  | Very Low | 3
R003 | Operational & Business Continuity Risk | Non-adversarial | Service disruption and downtime; Loss of business operations; Customer dissatisfaction; Revenue loss | Vendor due diligence and compliance assessment (ISO 27001 A.15); Contractual compliance clauses and SLAs; Periodic audits and certifications review; Regulatory monitoring and reporting | V01 | Amazon Web Services | 3 | 5 | 15 | Mitigate | Multi-region Redundancy | IT Operations Manager | Medium | 8
[5 empty] | V11 | Microsoft Azure | 3 | 5 | 15 | Mitigate | Disaster Recovery, failover systems |  | Medium | 8
[5 empty] | V02 | Temenos | 3 | 5 | 15 | Mitigate | Backup core banking systems |  | Medium | 8
[5 empty] | V03 | Razorpay | 3 | 5 | 15 | Mitigate | Backup payment gateway |  | Medium | 8
[5 empty] | V06 | Cloudflare | 3 | 4 | 12 | Mitigate | Content Delivery Network failover |  | Low | 6
[5 empty] | V08 | Twilio | 3 | 4 | 12 | Mitigate | Alternate communication channels |  | Low | 6
R004 | Cloud Service Outage | Non-adversarial | Service Unavailability; Transaction failures; SLA breaches; Business interruption | Multi-region deployment (for Amazon Web Services, Microsoft Azure); Auto-scaling and load balancing; Backup and restore procedures; Vendor SLA monitoring | V01 | Amazon Web Services | 3 | 5 | 15 | Mitigate | Multi-region deployment | IT Infrastructure Head | Medium | 8
[5 empty] | V11 | Microsoft Azure | 3 | 5 | 15 | Mitigate | Disaster recovery setup |  | Medium | 8
[5 empty] | V06 | Cloudflare | 3 | 4 | 12 | Mitigate | Traffic rerouting |  | Low | 6
R005 | API Integration Failure | Non-adversarial | Failed or delayed transactions; Data synchronization issues; Broken user workflows | API monitoring and logging (A.12); Retry and fallback mechanisms;cVersion control and testing; Rate limiting and timeout handling |  | Plaid | 4 | 5 | 20 | Mitigate | API Monitoring | IT Operations Manager/engineering lead | High | 12
[5 empty] | V08 | Twilio | 3 | 4 | 12 | Mitigate | Failover APIs |  | Low | 6
[5 empty] | V03 | Razorpay | 3 | 5 | 15 | Mitigate | Webhook retries, fallback |  | Medium | 8
R006 | Payment Fraud | Adversarial | Financial losses; Chargebacks and penalties; Legal implications; Loss of customer trust | Fraud detection and monitoring systems; Multi-factor authentication (A.9); Transaction limits and anomaly detection; Secure payment gateway integration | V03 | Razorpay | 4 | 5 | 20 | Mitigate | Fraud detection, MFA | Fraud Risk Manager | High | 12
R007 | Payment Gateway Failure | Non-adversarial | Service unavailability; failed transaction; Customer dissatisfaction | Backup payment gateway integration; Health monitoring of payment APIs; SLA agreements with vendor; Incident escalation procedures | V03 | Razorpay | 3 | 5 | 15 | Mitigate | Backup gateway + monitoring | IT Operations Manager | Medium | 8
R008 | KYC Verification Failure | Non-adversarial | Onboarding of fraudulent users; Regulatory non-compliance; Financial crime exposure; Legal penalties | Automated KYC validation (for Onfido); Periodic re-verification processes; Audit trails and logging (A.12); Compliance checks with regulatory standards | V07 | Onfido | 3 | 5 | 15 | Mitigate | Secondary verification + audit logs | Compliance Officer | Medium | 8
R009 | Physical Infrastructure Risk | Non-adversarial | Office inaccessibility; Operational disruption; Employee productivity loss; Safety concerns | Access control and surveillance (A.11); Emergency response procedures; Physical security policies; Backup work arrangements | V22 | WeWork | 2 | 3 | 6 | Accept | Remote work fallback | Administration Head | Very Low | 2
R010 | Data Breach & Cyber Attack | Adversarial | Exposure of sensitive data; Regulatory penalties; Financial loss and remediation cost; Reputational damage | Data encryption at rest and in transit (A.10); Access control and least privilege (A.9); Security monitoring (SIEM tools like Splunk); Regular vulnerability assessments and patching | V01 | Amazon Web Services | 2 | 5 | 10 | Mitigate | Encryption + IAM controls | CISO | Low | 4
[5 empty] | V11 | Microsoft Azure | 2 | 5 | 10 | Mitigate | Security monitoring |  | Low | 4
[5 empty] | V05 | Salesforce | 3 | 4 | 12 | Mitigate | Access control + audit logs |  | Low | 6
[5 empty] | V16 | Zendesk | 3 | 4 | 12 | Mitigate | Data masking + access restriction |  | Low | 6
[5 empty] | V03 | Razorpay | 3 | 5 | 15 | Mitigate | Secure payment encryption |  | Medium | 8
[5 empty] | V07 | Onfido | 3 | 5 | 15 | Mitigate | Identity data protection controls |  | Medium | 8
R011 | Cloud Provider Dependency Risk | Non-adversarial | Limited flexibility or migration challenges; Increased costs; Single point of failure | Multi-cloud or hybrid strategy; Vendor diversification; Exit and migration planning; Contractual flexibility clauses | V01 | Amazon Web Services | 3 | 5 | 15 | Mitigate | Multi-cloud strategy | Vendor Risk Manager | Medium | 8
[5 empty] | V11 | Microsoft Azure | 3 | 5 | 15 | Mitigate | Vendor diversification |  | Medium | 8
R012 | Unauthorized Access | Adversarial | Data compromise; Account misuse; Privilege escalation; Security incidents | Role-based access control (RBAC) (A.9); Multi-factor authentication; Periodic access reviews; Identity and access management (IAM) | V01 | Amazon Web Services | 3 | 5 | 15 | Mitigate | IAM + MFA | InfoSec Head | Medium | 8
[5 empty] | V11 | Microsoft Azure | 3 | 5 | 15 | Mitigate | RBAC + MFA |  | Medium | 8
[5 empty] | V05 | Salesforce | 3 | 4 | 12 | Mitigate | Role-based access |  | Low | 6
[5 empty] | V13 | Microsoft 365 | 3 | 4 | 12 | Mitigate | Identity controls |  | Low | 6
[5 empty] | V16 | Zendesk | 3 | 4 | 12 | Mitigate | Access restrictions |  | Low | 6
R013 | Data Residency | Non-adversarial | Violation of data protection laws; Regulatory penalties; Legal complications; Restrictions on operations | Data localization policies; Region-specific data storage (AWS/Azure regions); Compliance with data protection laws; Data classification (A.8) | V01 | Amazon Web Services | 3 | 4 | 12 | Mitigate | Region-based storage | Compliance Officer | Low | 6
[5 empty] | V11 | Microsoft Azure | 3 | 4 | 12 | Mitigate | Data localization |  | Low | 6
[5 empty] | V09 | Plaid | 4 | 4 | 16 | Mitigate | Data transfer compliance |  | Medium | 8
[5 empty] | V07 | Onfido | 3 | 4 | 12 | Mitigate | Regional data controls |  | Low | 6
R014 | Human Error | Non-adversarial | Misconfiguration or data exposure; Process failures; Operational inefficiencies; Minor service disruptions | Employee training and awareness (A.7); Standard operating procedures (SOPs); Change management controls (A.12); Approval workflows |  | General Risk; Applies to all | 3 | 3 | 9 | Mitigate | Educational training, SOPs, Automation | HR + IT Operations Manager | Very Low | 3
R015 | Incident Response Delay | Non-adversarial | Prolonged security incidents; Increased damage impact; Delayed recovery; Higher remediation costs | Incident response plan (A.16); 24/7 monitoring and alerting; Defined escalation matrix; Regular incident response drills | V01 | Amazon Web Services | 2 | 5 | 10 | Mitigate | Monitoring alerts | Security Operations Lead | Low | 4
[5 empty] | V11 | Microsoft Azure | 2 | 5 | 10 | Mitigate | Incident response setup |  | Low | 4
[5 empty] | V10 | Splunk | 2 | 4 | 8 | Mitigate | SIEM alerts |  | Very Low | 3
R016 | Third-party Subcontractor Risk | Non-adversarial | Loss of visibility and control; Indirect security vulnerabilities; Compliance gaps; Data exposure through fourth parties | Vendor risk assessment (A.15); Subcontractor disclosure requirements; Contractual security obligations; Continuous vendor monitoring | V01 | Amazon Web Services | 3 | 4 | 12 | Mitigate | Vendor due diligence | Vendor Risk Manager | Low | 6
[5 empty] | V11 | Microsoft Azure | 3 | 4 | 12 | Mitigate | Third-party visibility |  | Low | 6
[5 empty] | V05 | Salesforce | 3 | 4 | 12 | Mitigate | Contractual controls |  | Low | 6
[5 empty] | V16 | Zendesk | 3 | 4 | 12 | Mitigate | Subprocessor review |  | Low | 6